## Amazing_Ecommerce_Website
Amazing E-commerce Website Project
Project Manager: Ly Trung Kien
| Members: | Le Duc Long
Ton Nu Tu Anh
Dang Tran Trung Hieu
Nghiem Thi Xuan Thuy
Task ID | Completed At | Name | Section/Column | Assignee | Assignee Email | Start Date | Due Date | Tags | Notes | Projects | Parent Task | Priority
1200167328720120 |  | Specifies Requirement Description | Requirement | Dang Tran Trung Hieu | 1701040053@s.hanu.edu.vn | 2021-01-25 | 2021-01-26 |  |  | Amazing E-commerce Website |  | High
1200167328720120 |  | Draw Use case Diagram | Requirement | Ly Trung Kien | 1801040115@s.hanu.edu.vn | 2021-01-27 | 2021-01-29 |  |  | Amazing E-commerce Website |  | Medium
1200167328720130 |  | Written Use Case Specification | Requirement | Ly Trung Kien, Dang Tran Trung Hieu, Nghiem Thi Xuan Thuy, Ton Nu Tu Anh |  | 2021-01-27 | 2021-01-29 |  |  | Amazing E-commerce Website |  | Medium
1200167328720130 |  | Draw Activity Diagrams | Requirement | Nghiem Thi Xuan Thuy | 180104021@s.hanu.edu.vn | 2021-01-29 | 2021-02-02 |  |  | Amazing E-commerce Website |  | High
1200167328720140 |  | Draw Entity Relationship Diagram | Requirement | Ly Trung Kien | 1801040115@s.hanu.edu.vn | 2021-01-29 | 2021-02-02 |  |  | Amazing E-commerce Website |  | Medium
1200167329159840 |  | Mockups and Prototype | Requirement | Ton Nu Tu Anh |  | 2021-02-02 | 2021-02-09 |  |  | Amazing E-commerce Website |  | High
1200167329159840 |  | System Architecture | Analysis and Design | Le Duc Long, Ly Trung Kien |  |  | 2021-02-09 |  |  | Amazing E-commerce Website |  | Medium
1200167329159840 |  | UI Design | Analysis and Design | Ton Nu Tu Anh |  |  | 2021-02-09 |  |  | Amazing E-commerce Website |  | High
1200167329159840 |  | Database Design | Analysis and Design | Le Duc Long, Ly Trung Kien | 1701040013@s.hanu.edu.vn | 2021-02-10 | 2021-02-12 |  |  | Amazing E-commerce Website |  | High
1200167329159850 |  | Draw Class Diagram | Analysis and Design | Le Duc Long | 1801040130@s.hanu.edu.vn | 2021-02-10 | 2021-02-11 |  |  | Amazing E-commerce Website |  | Medium
1200167329159850 |  | Draw Sequence Diagrams | Analysis and Design | Dang Tran Trung Hieu |  | 2021-02-10 | 2021-02-13 |  |  | Amazing E-commerce Website |  | Medium
1200167329159850 |  | Back-end for customer site | Implementation | Le Duc Long, Ly Trung Kien |  | 2021-03-13 | 2021-03-16 |  |  | Amazing E-commerce Website |  | High
1200167329159860 |  | Back-end for administrator site | Implementation | Le Duc Long, Ly Trung Kien |  | 2021-03-20 | 2021-03-25 |  |  | Amazing E-commerce Website |  | High
1200167329159860 |  | Front-end for customer site | Implementation | Le Duc Long, Ly Trung Kien |  | 2021-03-16 | 2021-03-19 |  |  | Amazing E-commerce Website |  | High
1200167329159860 |  | Front-end for Administrator site | Implementation | Ton Nu Tu Anh |  | 2021-03-25 | 2021-03-29 |  |  | Amazing E-commerce Website |  | High
1200167329159860 |  | Database export | Implementation | Le Duc Long |  |  | 2021-03-29 |  |  | Amazing E-commerce Website |  | Medium
1200167329159860 |  | User Manuals | Implementation | Ton Nu Tu Anh |  |  | 2021-03-30 |  |  | Amazing E-commerce Website |  | Medium
1200167329159870 |  | Administrator Manuals | Implementation | Ton Nu Tu Anh |  |  | 2021-03-30 |  |  | Amazing E-commerce Website |  | Medium
1200167329159870 |  | Implement test case | Verification and Validation | Le Duc Long, Ly Trung Kien | [5 empty] | Amazing E-commerce Website |  | High
1200167329159870 |  | Write Test Report | Verification and Validation | Le Duc Long, Ly Trung Kien | [5 empty] | Amazing E-commerce Website |  | High
1200167329159870 |  | Write Code Inspection Report | Verification and Validation | Ly Trung Kien |  | 2021-03-30 | 2021-04-01 |  |  | Amazing E-commerce Website |  | Medium
1200167329159880 |  | Write SQA Plan | Verification and Validation | Dang Tran Trung Hieu |  | 2021-03-30 | 2021-04-01 |  |  | Amazing E-commerce Website |  | Medium
1200167329159880 |  | Application deployment | Deployment | Le Duc Long |  |  | 2021-04-10 |  |  | Amazing E-commerce Website |  | High
1200167329159880 |  | Write Project Plan | Project Management | Ly Trung Kien |  |  | 2021-01-25 |  |  | Amazing E-commerce Website |  | High
1200167329159880 |  | Write Activity Report | Project Management | Ly Trung Kien |  |  | 2021-04-09 |  |  | Amazing E-commerce Website |  | High
1200167329159890 |  | Slides | Presentation | Le Duc Long, Ton Nu Tu Anh, Nghiem Thi Xuan Thuy |  |  | 2021-04-09 |  |  | Amazing E-commerce Website |  | Medium
1200167329159890 |  | Demo video | Presentation | Le Duc Long, Ton Nu Tu Anh |  |  | 2021-04-10 |  |  | Amazing E-commerce Website |  | Medium